## Munka1
xx
| DANUrB+ TIMELINE |  | P1 |  | P2 |  |  | P3 |  |  | P4 |  | P5
|  | Meeting code (M) | M11 | M12 | M20 | M21 | M22 | M31 | M32 | M40 | M41 | M42 | M51 | M52
|  | Meeting date | 2020.09.25.-26. | 2020-11-27 | 2021-01-02 | 2021-03-04 | 2021-05-06 | 2021-07-08 | 2021-10-01 | 2022-01-02 | 2022-03-04 | 2022-06-07 | 2022-09-10 | 2022-11-01 | 11 trip scheduled | 35 days
Planned Days
|  | PLANNED INTERNATIONAL EVENTS SCHEDULE | Online Kick-off | Online Partners Meeting | EXTRA | Bratislava Partner Meeting + Budapest - Bratislava: Shrinking City Trip + Western European study tour SCOM | Timisoara meeting with Iron Gates Trip + Danube Days festival | Western European ASP tour | Sofia meeting with Vidin-Ruse boat trip + Partner Meeting | EXTRA | Belgrad-Novi Sad + Osijek Partners Meeting | Brăila-Galați-Tulcea | Bucharest-Călărași meeting | Closing event in Budapest + Ráckeve
|  | NEW PROPOSAL with ERASMUS+ |  | 2021-03-04: professors meeting; 2021-05-06: Belgrad - DANUrB Partner Meeting + DANUrB shrinking city tour in Section 2 (Zimbor? Hr?) Novi Sad meeting - Erasmus+ student trip? Plus DT.2.2.1; 2021-10-01: Bucharest - DANUrB Partner Meeting + DANUrB shrinking city tour (Calarasi, Giurgiu) + Erasmus+ student trip? + DT.2.2.1; 2022-03-04: Timisoara meeting with Iron Gates + Orsova + Moldova Nova + DT.2.2.1 international students workshop; 2022-06-07: Plus option for missing Deliverables; 2022-09-10: Sofia - VIdin - Ruse
| INTERNATIONAL EVENTS | Partner Meeting
|  | SCOM (5) | SCOM | 2021-03-04: SCOM; 2021-07-08: SCOM; 2022-06-07: SCOM; 2022-11-01: SCOM
|  | Shrinking Cities Study Trip (3) D.T.1.2.3. On-site research on study trips in each section of the Danube to document the effects of peripheral shrinking situation |  | 2021-03-04: Shrinking Cities Study Trip (3) D.T.1.2.3. On-site research on study trips in each section of the Danube to document the effects of peripheral shrinking situation; 2021-05-06: Shrinking Cities Study Trip (3) D.T.1.2.3. On-site research on study trips in each section of the Danube to document the effects of peripheral shrinking situation; 2021-10-01: Shrinking Cities Study Trip (3) D.T.1.2.3. On-site research on study trips in each section of the Danube to document the effects of peripheral shrinking situation
|  | Western European Study Trip (2) D.T.1.2.2. On-site research on study trips to good practice towns for studying development potentials in shrinking cities |  | 2021-03-04: Western European Study Trip D.T.1.2.2. On-site research on study trips to good practice towns for studying development potentials in shrinking cities; 2021-07-08: Western European Study Trip D.T.1.2.2. On-site research on study trips to good practice towns for studying development potentials in shrinking cities
|  | D.C.3.2.1 Project Conferences - incuding the kick-off and Final Closing conference | D.C.3.2.1 Project Conferences - incuding the kick-off and Final Closing conference | 2022-11-01: D.C.3.2.1 Project Conferences - incuding the kick-off and Final Closing conference
|  | D.C.3.3 Press conferences and annual press releases | D.C.3.3 Press conferences and annual press releases | 2021-05-06: D.C.3.3 Press conferences and annual press releases; 2022-11-01: D.C.3.3 Press conferences and annual press releases
|  | D.T. 3.2.2. International conference on the local values and initiatives along the Danube, with all good practices and forming stakeholder networks invited aiming to build a common Brand |  | 2021-03-04: D.T. 3.2.2. International conference on the local values and initiatives along the Danube, with all good practices and forming stakeholder networks invited aiming to build a common Brand; 2021-07-08: D.T. 3.2.2. International conference on the local values and initiatives along the Danube, with all good practices and forming stakeholder networks invited aiming to build a common Brand
The project intervention logic of DANUrB+ is the following: the first DANUrB identified local stakeholders to work with and local heritage to be valorized, giving a Strategy to make the valorizuation process succesful by making cooperative valorization and an interregional network of such heritage. DANUrB+ gives capacity building to stakeholders enabling them to make the valorization process, to cooperate locally and to be part of regional and interregional networks. DANUrB+ will give Action Plans at the local and regional level to define which heritage valorization processes will be most beneficial in peripheral and shrinking regions, and how to connect these culturally and spatially to form competitive regions At the largest scale DANUrB+ proposed interregional networks between such projects, and will initiate to network all independent initiatives working on the scope to valorize Danube's heritage to work in a coordinated way according to a Danube Cultural Promenade Action Plan.